## Slide 1
oxic
anoxic
oxic
anoxic
DOC (60 mL)
Fe (ferrozine; 10)
Fe-OC in sediment
pH (20 mL)
oxygen
21 days
o-o and a-a
7 days x 3 x 2 = 42
o-a and a-o
10 days x 3 x 2 = 60
Wednesday (sample reservoir, set up incubation)
  Take 4 sediment samples
  4 iron measurements, 4 DOC samples
  DO, pH
Friday (sample day 2)
Tuesday (sample day 6)
Friday (sample day 9)
Tuesday (sample day 13) - switch the o-a and a-o bottles
  For o-a this means bringing them all (n = 15) up to the anaerobic chamber
Wednesday (14)- switch only
Thursday (15) – switch only
Friday (sample day 16)
Tuesday (sample day 20)
Friday (sample day 23)
Tuesday extra sampling???
set up more o-a and a-o

## Slide 2: DOC sampling
~40 mL of water (10-15 required, plus some need reps)
Freeze this in a nutrient bottle

## Slide 3: Fe sampling
10 mLs
If you only care about total iron: just take a sample and acidify to pH 1-2. Should be stable for 6 months
Think about doing ferrozine for Fe2+
Total and soluble?
  Filters and tubes (order these)
  Do ferrozine a few (~3) times

## Slide 4: Set up
175 mls, 15 mls of sed using syringe

## Slide 5: pH
measure pH in separate bottle?

## Slide 6: Sediment
Need to clean out bottle and get it into a container that can be frozen
Syringe/pour out water
Use some scraper to get sediment out

## Slide 7: Oxygen
DO probe

## Slide 8: TO DO
Labels for metals samples
Box for frozen samples

## Slide 9: Ordering needs
Ordered
  Jars and lids
Things we have
  Syringes (normal acid washed)
  Scrapers (probably use metal ones from lab)
  Container to freeze sediment in (probably EEMs vials)
Other – for later
  Falcon tubes!